## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a student, I want to register and create a student profile so that the system securely stores my academic credentials, department, and academic year. | MUST HAVE | None | Pranav Deshmukh | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a student, I want to take a structured technical skill assessment quiz so that the platform can establish my technical baseline and competencies. | MUST HAVE | US-01 | Abhishek Bhosale | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a student, I want to submit a 2-3 line project idea and domain area in a clean split-screen UI to trigger automated blueprint generation. | MUST HAVE | US-01 | Afreen Shaik | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a developer, I want a decoupled database schema in Supabase PostgreSQL for students, skills, and project proposals to ensure data normalization. | MUST HAVE | None | Manasa Bethampudi | 3- Completed
Sprint 2 | Sprint 2 | US-05 | As a student, I want the Feasibility Analysis Agent to evaluate technical depth, resource requirements, and timeline realism from my rough idea. | MUST HAVE | US-03, US-04 | Pranav Deshmukh | 3- Completed
Sprint 2 | Sprint 2 | US-06 | As a student, I want the Scope Definition Agent to clarify project boundaries, core requirements, and stretch goals without manual prompting. | MUST HAVE | US-05 | Abhishek Bhosale | 3- Completed
Sprint 2 | Sprint 2 | US-07 | As a student, I want the Tech Stack Recommendation Agent to recommend suitable frameworks, libraries, and databases with trade-off justification. | MUST HAVE | US-02, US-06 | Manasa Bethampudi | 3- Completed
Sprint 2 | Sprint 2 | US-08 | As a student, I want the Milestone & Timeline Planning Agent to generate a week-wise execution roadmap with Mermaid Gantt charts. | MUST HAVE | US-06, US-07 | Afreen Shaik | 3- Completed
Sprint 2 | Sprint 2 | US-09 | As a team, we want to validate the initial 7-agent sequential LangGraph pipeline using sample student project ideas for end-to-end integrity. | MUST HAVE | US-05, US-06, US-07, US-08 | Pranav Deshmukh | 3- Completed
Sprint 3 | Sprint 3 | US-10 | As a student, I want the Risk Assessment Agent to identify execution bottlenecks, third-party dependencies, and provide actionable mitigation steps. | MUST HAVE | US-07, US-08 | Abhishek Bhosale | 3- Completed
Sprint 3 | Sprint 3 | US-11 | As a student, I want to upload syllabus and rubric PDF documents to Pinecone vector DB so that AI responses are context-aware (RAG). | SHOULD HAVE | US-03, US-04 | Manasa Bethampudi | 3- Completed
Sprint 3 | Sprint 3 | US-12 | As a student, I want a conversational mentor chat workspace for ongoing technical queries, debugging guidance, and architecture questions. | MUST HAVE | US-09, US-11 | Afreen Shaik | 3- Completed
Sprint 4 | Sprint 4 | US-13 | As a student, I want to submit weekly progress updates so that the AI pipeline automatically dynamically recalibrates my project schedule. | MUST HAVE | US-08, US-12 | Pranav Deshmukh | 3- Completed
Sprint 4 | Sprint 4 | US-14 | As a student, I want to generate a standardized Academic Project Synopsis on demand formatted according to university standards. | MUST HAVE | US-09, US-13 | Abhishek Bhosale | 3- Completed
Sprint 4 | Sprint 4 | US-15 | As a student, I want to generate a formal Methodology & System Architecture Document with detailed component flows. | MUST HAVE | US-14 | Manasa Bethampudi | 3- Completed
Sprint 4 | Sprint 4 | US-16 | As a student, I want to export generated progress reports and thesis outline documents in structured Markdown and PDF formats. | SHOULD HAVE | US-14, US-15 | Afreen Shaik | 3- Completed
Sprint 5 | Sprint 5 | US-17 | As a faculty mentor, I want a centralized monitoring dashboard to passively oversee all assigned student project teams and their progress. | MUST HAVE | US-01, US-09, US-13 | Pranav Deshmukh | 3- Completed
Sprint 5 | Sprint 5 | US-18 | As a faculty mentor, I want real-time project health indicators (Green/Amber/Red) and risk alerts to quickly identify lagging teams. | MUST HAVE | US-10, US-17 | Afreen Shaik | 3- Completed
Sprint 5 | Sprint 5 | US-19 | As a faculty mentor, I want auto-generated weekly executive summaries of student achievements and unresolved blockers. | SHOULD HAVE | US-13, US-17 | Manasa Bethampudi | 3- Completed
Sprint 6 | Sprint 6 | US-20 | As a team, we want comprehensive end-to-end system testing, prompt optimization, Groq fallback handling, and final demo preparation. | MUST HAVE | US-01 to US-19 | Abhishek Bhosale | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 342 | 342 | 326 | 297 | 250 | 212 | 173 | 132 | 98 | 80 | 66 | 53 | 32 | 10 | 0
SPRINT 1 BACKLOG
US-01 | T-101 | Study agentic AI workflows & multi-agent architectures (LangGraph/LangChain) | 2026-05-27 | 2026-05-29 | Pranav Deshmukh | Design | 3- Completed | 8 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-102 | Design normalized database schemas in Supabase (student, skills, project_idea) | 2026-05-28 | 2026-05-31 | Manasa Bethampudi | Design | 3- Completed | 10 | 10 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-103 | Implement student registration & JWT authentication APIs in FastAPI | 2026-05-30 | 2026-06-03 | Pranav Deshmukh | Coding | 3- Completed | 12 | 12 | 12 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-104 | Develop skill assessment quiz UI components and dynamic scoring logic in React | 2026-06-01 | 2026-06-04 | Abhishek Bhosale | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-105 | Build premium split-screen project idea submission interface with dark/light themes | 2026-06-02 | 2026-06-05 | Afreen Shaik | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-106 | Implement Supabase client wrapper and database upsert routines in backend | 2026-06-03 | 2026-06-06 | Manasa Bethampudi | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-107 | Execute unit testing and validation for onboarding and database roundtrip | 2026-06-06 | 2026-06-08 | Abhishek Bhosale | Unit Test | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0
US-03 | T-108 | Conduct Milestone 1 demonstration & prepare submission documentation | 2026-06-08 | 2026-06-09 | Afreen Shaik | Others | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
US-05 | T-201 | Implement Feasibility Analysis Agent with structured LLM prompt engineering | 2026-06-10 | 2026-06-13 | Pranav Deshmukh | Coding | 3- Completed | 10 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-202 | Develop Scope Definition Agent to separate core MVP vs stretch deliverables | 2026-06-11 | 2026-06-14 | Abhishek Bhosale | Coding | 3- Completed | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-203 | Build Technology Stack Recommendation Agent with trade-off justification logic | 2026-06-13 | 2026-06-16 | Manasa Bethampudi | Coding | 3- Completed | 10 | 10 | 10 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-204 | Develop Milestone & Timeline Planning Agent with Mermaid Gantt generation | 2026-06-15 | 2026-06-18 | Afreen Shaik | Coding | 3- Completed | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-205 | Construct LangGraph state machine orchestrating sequential 7-agent execution | 2026-06-17 | 2026-06-20 | Pranav Deshmukh | Build | 3- Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0
US-09 | T-206 | Validate end-to-end pipeline outputs against diverse student benchmark ideas | 2026-06-20 | 2026-06-22 | Abhishek Bhosale | System Test | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
US-08 | T-207 | Build UI tabs in React/Streamlit for Feasibility, Scope, Stack, and Timeline | 2026-06-21 | 2026-06-23 | Afreen Shaik | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0
US-10 | T-301 | Develop Risk Assessment & Mitigation Agent to evaluate blockers & contingency | 2026-06-24 | 2026-06-27 | Abhishek Bhosale | Coding | 3- Completed | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-302 | Setup Pinecone vector database index & SentenceTransformers embedding pipeline | 2026-06-25 | 2026-06-28 | Manasa Bethampudi | Build | 3- Completed | 10 | 10 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-303 | Build PDF upload & document chunking API endpoint for syllabus/rubrics (/upload) | 2026-06-27 | 2026-06-30 | Manasa Bethampudi | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-304 | Develop conversational AI Mentor chat endpoint (/chat) with LangChain RAG | 2026-06-29 | 2026-07-02 | Pranav Deshmukh | Coding | 3- Completed | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-305 | Build interactive Mentor Chat UI workspace with real-time streaming & citations | 2026-07-01 | 2026-07-04 | Afreen Shaik | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0
US-10 | T-306 | Perform integration testing for RAG vector retrieval and conversational mentor | 2026-07-04 | 2026-07-07 | Abhishek Bhosale | Integration Test | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0
US-13 | T-401 | Implement dynamic progress update API (/progress_update) with plan recalibration | 2026-07-08 | 2026-07-11 | Pranav Deshmukh | Coding | 3- Completed | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-402 | Develop weekly mentor check-in agent endpoint (/check_in) for milestone goals | 2026-07-10 | 2026-07-13 | Abhishek Bhosale | Coding | 3- Completed | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-403 | Build Academic Project Synopsis generation prompt engine and endpoint | 2026-07-12 | 2026-07-15 | Abhishek Bhosale | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-404 | Develop Methodology and System Architecture Document generation module | 2026-07-14 | 2026-07-17 | Manasa Bethampudi | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-405 | Build Document Generator UI with preview, markdown rendering, & file downloads | 2026-07-16 | 2026-07-19 | Afreen Shaik | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0 | 0 | 0 | 0
US-14 | T-406 | Validate document formatting against university academic project rubrics | 2026-07-19 | 2026-07-21 | Pranav Deshmukh | System Test | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0
US-17 | T-501 | Build aggregated faculty dashboard endpoint (/faculty/dashboard) in FastAPI | 2026-07-22 | 2026-07-25 | Pranav Deshmukh | Coding | 3- Completed | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-502 | Implement automated project health heuristics (Green/Amber/Red) & risk flags | 2026-07-24 | 2026-07-27 | Abhishek Bhosale | Coding | 3- Completed | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-503 | Build auto-generated mentor weekly executive summary generation service | 2026-07-26 | 2026-07-29 | Manasa Bethampudi | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-504 | Develop responsive Faculty Dashboard UI with project table, filters & metrics | 2026-07-28 | 2026-07-31 | Afreen Shaik | Coding | 3- Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-505 | Perform cross-module integration across all 8 modules and database views | 2026-08-01 | 2026-08-04 | Pranav Deshmukh | Integration Test | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
US-20 | T-601 | Optimize prompt engineering & implement Groq fallback on Gemini rate limits | 2026-08-05 | 2026-08-09 | Pranav Deshmukh | Coding | 3- Completed | 10 | 10 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-602 | Implement Mermaid diagram regex extraction wrapper for bulletproof UI rendering | 2026-08-08 | 2026-08-12 | Afreen Shaik | Coding | 3- Completed | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-603 | Conduct end-to-end regression testing across all 7 agents and edge case inputs | 2026-08-11 | 2026-08-15 | Abhishek Bhosale | Regression Test | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-604 | Perform database index tuning & query optimization for Supabase & Pinecone | 2026-08-14 | 2026-08-18 | Manasa Bethampudi | Build | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
US-20 | T-605 | Compile comprehensive technical documentation, architecture report, & user guide | 2026-08-17 | 2026-08-21 | Afreen Shaik | Others | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
US-20 | T-606 | Conduct final system verification against all 5 evaluation criteria & demo rehearsal | 2026-08-20 | 2026-08-24 | Abhishek Bhosale | System Test | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Slow initial Supabase connection setup when executing raw SQL from backend. | Configured Supabase Python SDK client with connection pooling and secure environment variables.
Sprint 1 | Day 5 | Frontend CORS rejection when sending JSON payload from Vite (port 5173) to FastAPI (port 8000). | Added CORSMiddleware in api.py with allow_origins=['*'], allow_credentials=True, allow_methods=['*'].
Sprint 1 | Day 8 | Student skill assessment payload failing schema validation when skill array was empty. | Added Pydantic validator default values and client-side form validation before submitting /onboard.
Sprint 1 | Day 12 | Frontend state desynchronization between onboarding form submission and verification transcript. | Added 1-second auto-poll and verification callback to GET /student/{id} to refresh client state.
Sprint 2 | Day 3 | Feasibility Agent prompt occasionally returning non-JSON unstructured text from Gemini. | Enforced strict JSON schema output formatting and wrapped parser in Pydantic BaseModel.
Sprint 2 | Day 7 | Mermaid Gantt chart code syntax errors generated by Planner Agent causing UI render crash. | Sanitized LLM output with regex pattern to strip backticks and validate Mermaid syntax tokens.
Sprint 2 | Day 10 | Tech Stack Advisor recommending obsolete library versions for specialized ML domains. | Enhanced prompt with updated 2026 tech stack knowledge and domain constraints.
Sprint 2 | Day 13 | Sequential 7-agent pipeline execution exceeding 90 seconds, risking HTTP gateway timeout. | Configured async agent node dispatch in LangGraph and set frontend Axios timeout to 300 seconds.
Sprint 3 | Day 2 | Pinecone index vector dimension mismatch between SentenceTransformers (384-d) and index (1536-d). | Recreated Pinecone serverless index with exact 384 dimensions matching all-MiniLM-L6-v2 embedding model.
Sprint 3 | Day 6 | PDF upload extraction throwing encoding errors on complex mathematical symbols in rubrics. | Switched to PyPDF / pdfplumber with UTF-8 character normalization and text chunking overlapping by 100 tokens.
Sprint 3 | Day 9 | Mentor chat responses lacking project context when student asked follow-up implementation questions. | Injected student's active project idea, tech stack, and retrieved Pinecone context into LangChain system prompt.
Sprint 3 | Day 13 | Conversational UI chat window scrolling jumpy during streaming LLM token generation. | Optimized React chat container with smooth auto-scroll to bottom ref behavior on token reception.
Sprint 4 | Day 3 | Progress update agent occasionally overwriting completed tasks in the week-wise plan. | Modified plan revision prompt to strictly mark past weeks as completed and only reschedule remaining weeks.
Sprint 4 | Day 7 | Generated Synopsis document lacking university-standard section headers (Aim, Scope, Methodology). | Created structured academic markdown templates with explicit placeholder injection for each section.
Sprint 4 | Day 11 | Client-side export to Markdown creating unformatted plain text on Windows OS. | Added proper MIME type 'text/markdown' and UTF-8 BOM encoding for seamless cross-platform downloads.
Sprint 5 | Day 3 | Faculty dashboard API query taking >3 seconds when fetching 25+ student project records. | Created an optimized PostgreSQL materialized view in Supabase joining student, project, and checkin summaries.
Sprint 5 | Day 8 | Project health status algorithm misclassifying projects with early setbacks as Red critical. | Refined heuristic algorithm to weigh recent check-in sentiment and milestone velocity alongside overdue tasks.
Sprint 5 | Day 12 | Faculty UI table layout breaking on mobile and tablet viewport resolutions. | Implemented responsive Tailwind CSS grid with collapsible rows and mobile-friendly summary cards.
Sprint 6 | Day 4 | Occasional 429 Too Many Requests rate-limit errors from Gemini API during heavy test runs. | Integrated automated fallback routing to Groq (LLaMA 3 70B) with exponential backoff retries.
Sprint 6 | Day 10 | Discrepancy in project blueprint generation quality when student entered <10 words. | Added intelligent input expander pre-prompt that enriches brief ideas before triggering the main 7 agents.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-05-27 | 2026-06-09 | Pranav Deshmukh | Modularizing API routing early and creating strict Pydantic schemas. | Coupling database queries directly with frontend UI handlers. | Using decoupled architecture between FastAPI backend and React frontend. | Separated backend API gateway from agent pipeline and established Supabase normalized tables.
2 | Sprint 1 | 2026-05-27 | 2026-06-09 | Manasa Bethampudi | Writing schema migration scripts in SQL before building application endpoints. | Hardcoding connection strings and API credentials in local files. | Using .env configuration with comprehensive .env.example documentation. | Created database schemas in Supabase and secured API keys in backend environment.
3 | Sprint 1 | 2026-05-27 | 2026-06-09 | Abhishek Bhosale | Writing unit test assertions for all schema edge cases (empty skills, special chars). | Manual regression testing without automated test scripts. | Automated test plans with clear condition and expected result definitions. | Created initial unit test suite verifying student onboarding and profile retrieval.
4 | Sprint 1 | 2026-05-27 | 2026-06-09 | Afreen Shaik | Designing human-crafted, split-screen UI layouts with dark/light mode themes. | Using generic, standard template cards without interactive micro-animations. | Consistent color palettes, Tailwind tokens, and responsive layout grids. | Implemented premium split-screen student onboarding interface with smooth micro-interactions.
5 | Sprint 2 | 2026-06-10 | 2026-06-23 | Pranav Deshmukh | Using LangGraph state machine to handle agent transitions and shared memory. | Writing monolithic agent functions without isolated role prompts. | Decomposing complex mentoring into specialized, modular agent nodes. | Constructed 7-agent sequential LangGraph pipeline with structured JSON outputs.
6 | Sprint 2 | 2026-06-10 | 2026-06-23 | Abhishek Bhosale | Testing agent outputs with intentionally ambiguous and complex project prompts. | Assuming LLMs will always return syntactically valid Mermaid diagrams. | Validating LLM outputs with Pydantic and regex sanitizers before UI rendering. | Implemented output validation and verified Feasibility and Scope agents across 10 sample ideas.
7 | Sprint 3 | 2026-06-24 | 2026-07-07 | Manasa Bethampudi | Chunking PDFs with semantic sentence overlap to preserve context during embedding. | Uploading full unchunked documents directly to vector databases. | Using SentenceTransformers for fast, cost-effective local vector embeddings. | Integrated Pinecone serverless vector database and built PDF ingestion pipeline for RAG.
8 | Sprint 3 | 2026-06-24 | 2026-07-07 | Afreen Shaik | Implementing streaming UI responses with clear source citations for RAG chat. | Blocking the UI while waiting for entire conversational responses to complete. | Clean chat bubbles with Markdown formatting and copy-to-clipboard actions. | Delivered conversational mentoring chat interface with real-time feedback and document references.
9 | Sprint 4 | 2026-07-08 | 2026-07-21 | Pranav Deshmukh | Maintaining milestone state history so plan adjustments only impact future weeks. | Wiping entire project schedules when students submit minor progress delays. | Dynamic plan recalibration that preserves completed milestones and adjusts remaining tasks. | Built dynamic progress tracking and week-wise project plan adjustment engine.
10 | Sprint 4 | 2026-07-08 | 2026-07-21 | Abhishek Bhosale | Standardizing academic document templates against standard university project rubrics. | Generating generic text without academic structure (Synopsis, Methodology, Progress). | Providing downloadable, beautifully formatted Markdown files. | Developed automated document generation module for Synopsis, Methodology, and Progress reports.
11 | Sprint 5 | 2026-07-22 | 2026-08-04 | Manasa Bethampudi | Creating database aggregate views for high-performance dashboard analytics. | Executing N+1 separate queries for every student card on the faculty dashboard. | Caching computed project health scores and summary metrics. | Engineered optimized backend queries and data aggregations for faculty project monitoring.
12 | Sprint 5 | 2026-07-22 | 2026-08-04 | Afreen Shaik | Using color-coded health badges (Green/Amber/Red) and quick filter cards for mentors. | Overwhelming faculty with raw JSON data instead of visual executive summaries. | Clean tabular views with modal drill-downs into individual student project blueprints. | Built intuitive Faculty Monitoring Dashboard with real-time project health indicators.
13 | Sprint 6 | 2026-08-05 | 2026-08-24 | Pranav Deshmukh | Implementing automated fallback mechanisms (Groq/Gemini) to guarantee 99.9% uptime. | Relying on a single LLM provider without timeout handling or rate limit fallbacks. | Conducting thorough latency and load testing before milestone defense. | Configured multi-model resilience with Groq fallback and finalized system architecture.
14 | Sprint 6 | 2026-08-05 | 2026-08-24 | Abhishek Bhosale | Executing end-to-end regression test plans covering all 8 modules and 5 evaluation criteria. | Leaving edge cases untested until final presentation day. | Documenting all defects with root cause analysis and permanent code fixes in defect tracker. | Completed full system regression testing, test plan documentation, and final defense preparation.