## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Abhishek Bhosale | 2026-05-30 | Student registration API accepts malformed email formats and empty password strings without returning a 422 HTTP error. | Sprint 1 | Pranav Deshmukh | Logical | Added Pydantic EmailStr field validation and regex password complexity check in auth router. | 2026-05-31 | Closed | Verified with test case TC_AUTH_001; returns HTTP 422 for invalid payloads.
2 | Afreen Shaik | 2026-06-02 | Skills array in onboarding form crashes Supabase insert query when user deselects all skill options. | Sprint 1 | Manasa Bethampudi | Logical | Added null-coalescing fallback in backend schema to cast empty skills to empty JSON list []. | 2026-06-03 | Closed | Verified in Supabase student and skill_assessment tables; records commit successfully.
3 | Pranav Deshmukh | 2026-06-04 | Floating input labels on onboarding split-screen UI overlap with pre-filled browser autofill text in Chrome. | Sprint 1 | Afreen Shaik | User Interface | Updated Tailwind peer-focus CSS selectors and added autofill background transition override. | 2026-06-05 | Closed | Verified in Chrome, Firefox, and Edge under both Dark and Light themes.
4 | Manasa Bethampudi | 2026-06-07 | Environment variables in backend missing fallback defaults causing crash on unconfigured test machines. | Sprint 1 | Abhishek Bhosale | Maintainability | Created config.py module with Pydantic BaseSettings and default placeholders with clear warning logs. | 2026-06-08 | Closed | Tested startup with missing .env; server prints graceful configuration warnings.
5 | Abhishek Bhosale | 2026-06-12 | Feasibility Analysis Agent occasionally outputs unstructured narrative text instead of required JSON keys. | Sprint 2 | Pranav Deshmukh | Logical | Injected strict JSON schema constraints in Gemini system prompt and added Pydantic output parsing wrapper. | 2026-06-13 | Closed | Tested with 20 sample project proposals; 100% JSON parsing compliance achieved.
6 | Afreen Shaik | 2026-06-16 | Milestone & Timeline Agent generates invalid Mermaid Gantt chart syntax (unescaped colons in task names). | Sprint 2 | Afreen Shaik | User Interface | Implemented regex sanitizer in frontend Mermaid rendering wrapper to escape special characters. | 2026-06-17 | Closed | Verified Gantt chart renders cleanly without syntax parse exceptions in UI.
7 | Manasa Bethampudi | 2026-06-19 | Sequential 7-agent pipeline execution in /initialize times out on frontend after 60s default Axios limit. | Sprint 2 | Pranav Deshmukh | Logical | Increased Axios client timeout to 300s and added animated progress spinner with status text. | 2026-06-20 | Closed | End-to-end pipeline completes reliably within ~90s without connection drops.
8 | Pranav Deshmukh | 2026-06-21 | Tech Stack Recommendation Agent hardcoding Python 3.8 and obsolete TensorFlow 2.4 suggestions. | Sprint 2 | Abhishek Bhosale | Standards | Updated system prompt context with current 2026 technology standards (PyTorch 2.x, Next.js 14, FastAPI). | 2026-06-22 | Closed | Verified modern tech stack outputs across Web, AI/ML, IoT, and Cloud domains.
9 | Abhishek Bhosale | 2026-06-26 | Pinecone vector upsert throws 400 Bad Request error due to 1536-dimension index vs 384-dimension embeddings. | Sprint 3 | Manasa Bethampudi | Logical | Reconfigured Pinecone serverless index to 384 dimensions matching all-MiniLM-L6-v2 model. | 2026-06-27 | Closed | PDF embeddings index and query successfully with cosine similarity scoring.
10 | Afreen Shaik | 2026-06-30 | PDF upload endpoint (/upload) crashes when processing multi-page PDFs with embedded scanned images. | Sprint 3 | Manasa Bethampudi | Logical | Added exception handling with fallback text extraction using pdfplumber and OCR error bypass. | 2026-07-01 | Closed | Ingested complex 15-page syllabus and grading rubrics without memory leaks.
11 | Pranav Deshmukh | 2026-07-03 | Mentor chat (/chat) hallucinates answers unrelated to student project when context retrieval is empty. | Sprint 3 | Pranav Deshmukh | Logical | Modified RAG prompt to inject student project blueprint as fallback context if similarity < 0.65. | 2026-07-04 | Closed | Verified grounded mentoring responses even with minimal uploaded documentation.
12 | Manasa Bethampudi | 2026-07-10 | Progress update endpoint (/progress_update) resets milestone completion dates for prior weeks. | Sprint 4 | Abhishek Bhosale | Logical | Updated prompt logic to preserve completed historical milestones and only reschedule pending tasks. | 2026-07-11 | Closed | Verified dynamic plan adjustment preserves Weeks 1-3 progress while extending Week 4-6 schedule.
13 | Afreen Shaik | 2026-07-14 | Academic Synopsis generator generates inconsistent heading structures across different runs. | Sprint 4 | Abhishek Bhosale | Standards | Implemented standardized Markdown template with fixed university headings (1. Introduction, 2. Objectives, etc.). | 2026-07-15 | Closed | 100% template compliance verified across Synopsis, Methodology, and Progress reports.
14 | Abhishek Bhosale | 2026-07-17 | Download button for generated documents downloads files with .txt extension instead of .md on Safari. | Sprint 4 | Afreen Shaik | User Interface | Set explicit Blob MIME type to 'text/markdown;charset=utf-8' and enforced file naming convention. | 2026-07-18 | Closed | Cross-browser download tested and verified on Chrome, Safari, Firefox, and Edge.
15 | Pranav Deshmukh | 2026-07-24 | Faculty dashboard query (/faculty/dashboard) triggers multiple sequential database requests causing UI lag. | Sprint 5 | Manasa Bethampudi | Maintainability | Created a single consolidated PostgreSQL SQL join query in Supabase with student, project, and checkin tables. | 2026-07-25 | Closed | Dashboard response latency reduced from 2.8s to 180ms.
16 | Afreen Shaik | 2026-07-28 | Faculty dashboard project cards overflow text when student enters exceptionally long project descriptions. | Sprint 5 | Afreen Shaik | User Interface | Added line-clamp-2 Tailwind utility and expandable modal for viewing complete project synopsis. | 2026-07-29 | Closed | Responsive grid cleanly handles 1 to 50 student projects across all device viewports.
17 | Abhishek Bhosale | 2026-08-07 | Rate limit 429 Too Many Requests errors from Gemini API during batch student initialization testing. | Sprint 6 | Pranav Deshmukh | Logical | Added automated fallback to Groq API (LLaMA 3 70B) with exponential backoff retry handler. | 2026-08-08 | Closed | Pipeline seamlessly switches to Groq when Gemini reaches rate limit thresholds.
18 | Manasa Bethampudi | 2026-08-15 | Database connection pool exhaustion during concurrent multi-user load testing. | Sprint 6 | Manasa Bethampudi | Maintainability | Implemented async connection context managers and tuned Supabase connection pool size to 20. | 2026-08-16 | Closed | Successfully passed load test with 50 concurrent simulated student requests.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others